## Cover
Revision History
Date | Version | Description | Creater
2019-10-04 | 1 | Add | DungND

## Config (hidden)
Pass | High
Fail | Medium
Untested | Low
Fix

## Test_Report
Test Report | [5 empty] | Project Name | Travel With Locals | Creator | DungND
Test coverage |  | 100 | % |  |  | Project Code | TWL | Reviewer/Approver | DangNG
Test successful coverage |  | 100 | % |  |  | Document Code |  | Issue Date
Notes
No | Module code | Pass | Fail | Untested | Number of test cases
1 | Manage guider contract | 17 | 0 | 0 | 17
2 | Search guider account | 3 | 0 | 0 | 3
3 | Manage guider account | 15 | 0 | 0 | 15
4 | Manage guider post | 11 | 0 | 0 | 11
5 | View/Hide review on a post | 8 | 0 | 0 | 8
6 | Add category | 10 | 0 | 0 | 10
7 | Add location | 18 | 0 | 0 | 18
8 | View statistic revenuew by month | 2 | 0 | 0 | 2
9 | View statistic revenuew of completed trip by month | 2 | 0 | 0 | 2
10 | Log in/Log out | 10 | 0 | 0 | 10
| Tổng | 96 | 0 | 0 | 96

## Manage guider contract
| Module Code | Manage guider contract
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 17 |  |  | 0 |  | 0 |  | 17 |  | 17 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Guider Contract page | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. Redirects to "Manage Guider Contarct" screen 2. Guider Contarct Management is shown, including: Name, Nationality, Date of birth, Gender, Home town, Address, Identity card number, Card issued date, Card issued province, Download file PDF, Accept, Reject. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DungND
2 | UI test | Check Display of Name column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. Name of Guider in Contract file uploaded should be displayed under "Name" column. |  | Pass | High |  |  | 08-10-2019 | DungND
3 | UI test | Check Display of Nationality column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. Nationality of Guider in Contract file uploaded should be displayed under "Nationality" column. |  | Pass | High |  |  | 08-10-2019 | DungND
4 | UI test | Check Display of Date of Birth column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Date of Birth" of Guider in Contract file uploaded should be displayed under "Date of Birth" column. |  | Pass | High |  |  | 08-10-2019 | DungND
5 | UI test | Check Display of Gender column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Gender" of Guider in Contract file uploaded should be displayed under "Gender" column. |  | Pass | High |  |  | 08-10-2019 | DungND
6 | UI test | Check Display of Hometown column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Howntown" of Guider in Contract file uploaded should be displayed under "Howntown" column. |  | Pass | High |  |  | 08-10-2019 | DungND
7 | UI test | Check Display of Card Issued date column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Card Issued date" of Guider in Contract file uploaded should be displayed under "Gender" column. |  | Pass | High |  |  | 08-10-2019 | DungND
8 | UI test | Check Display of Identity Card Number column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Identity Card Number" of Guider in Contract file uploaded should be displayed under "Identity Card Number" coulumn. |  | Pass | High |  |  | 08-10-2019 | DungND
9 | UI test | Check Display of Cars issued province column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. "Card issued province" of Guider in Contract file uploaded should be displayed under "Card issued province" coulumn |  | Pass | High |  |  | 08-10-2019 | DungND
10 | UI test | Check Display of Download file PDF column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. A button to download file pdf contained certificate and degree of Guider in Contract file uploaded should be displayed under "Download file PDF" column. |  | Pass | High |  |  | 08-10-2019 | DungND
11 | UI test | Check Display of Reject column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. A button to download file pdf contained certificate and degree of Guider in Contract file uploaded should be displayed under "Download file PDF" column. |  | Pass | High |  |  | 08-10-2019 | DungND
12 | UI test | Check Display of Accept column | 1. User clicks on "Manage Guider Contract" | Login admin'account |  | 1. REdirects to "Manage Guider Contarct" screen 2. A button to download file pdf contained certificate and degree of Guider in Contract file uploaded should be displayed under "Download file PDF" column. |  | Pass | High |  |  | 08-10-2019 | DungND
13 | Function test | Check function download file PDF | 1. User clicks on "Manage Guider Contract" 2. Click on "PDF" file under "Download file PDF" column 3. When pdf file is opened, click on button download in the right corner of the screen | Login guider's account |  | 1. A pdf file is opened in a new tab 2. When click on button download, a pdf file is downloaded. |  | Pass | High |  |  | 08-10-2019 | DungND
14 | Function test | Check function of "Accept" button under "Accept" column | 1. User clicks on "Manage Guider Contract" 2. Click on Accept button | Login guider's account |  | 1. Contract is accpeted. 2. The row is disappeared |  | Pass | High |  |  | 08-10-2019 | DungND
15 | Database test | Check result in database when click on "Accept" button under "Accept" column | 1. User clicks on "Manage Guider Contract" 2. Click on Accept button | Login guider's account |  | 1. Contract is acceped. 2. Guider table links with Contract detail in table "Contract" 3. Active_date in table "Contract_detail" is not null now and deactivated_date is null |  | Pass | High |  |  | 08-10-2019 | DungND
16 | Function test | Check function of "Reject" button under "Reject" column | 1. User clicks on "Manage Guider Contract" 2. Click on Reject button | Login guider's account |  | 1. Contract is rejected 2. The row is disappeared |  | Pass | High |  |  | 08-10-2019 | DungND
17 | Database test | Check result in database when click on "Reject" button under "Reject" column | 1. User clicks on "Manage Guider Contract" 2. Click on Reject button | Login guider's account |  | 1. Contract is rejected 2. Guider table links with Contract detail in table "Contract" 3. Active_date in table "Contract_detail" is still null and deactivated_date is not null. |  | Pass | High |  |  | 08-10-2019 | DungND

## Search Guider Account
| Module Code | Search guider account
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 3 |  |  | 0 |  | 0 |  | 3 |  | 2 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of search bar | 1.Open web | Login admin account |  | 1. Input area and button search as the design in SRS 2. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DangNG
2 | Function test | Search Guider name with key word is null | 1. Open admin website manager 2. Click on search icon on the side of the search bar 4. Input Guider key word into the search bar. 5. Click on "Search" button | Login admin account | Search for ''" | 1. Display all account name |  | Pass | High |  |  | 08-10-2019 | DangNG
3 | Function test | Search Guider account name | 1. Open admin website manager 2. Click on search icon on the side of the search bar 4. Input Guider key word into the search bar. 5. Click on "Search" button | Login admin'account | Search for ''He" | 1. Redirect to search result screen 2. A list of guider name is listed below. |  | Pass | High |  |  | 08-10-2019 | DangNG

## Manage Guider Account
| Module Code | Manage guider account
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 15 |  |  | 0 |  | 0 |  | 15 |  | 14 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Guider Account page | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Guider Contarct Account is shown, including: User name, Email, Role, Status, Activate button, Deactivate button. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DungND
2 | UI test | Check Display of Name column | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Name of Guider should be displayed under "Name" column. |  | Pass | High |  |  | 08-10-2019 | DungND
3 | UI test | Check Display of Email column | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Email of Guider should be displayed under "Email" column. |  | Pass | High |  |  | 08-10-2019 | DungND
4 | UI test | Check Display of Role column | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Role of Guider should be displayed under "Role" column. |  | Pass | High |  |  | 08-10-2019 | DungND
5 | UI test | Check Display of Status column | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Status of Guider should be displayed under "Status" column. |  | Pass | High |  |  | 08-10-2019 | DungND
6 | UI test | Check Display of Activate button | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Button "Accept" should be displayed in blue and in the same line with guider and next to Status column. |  | Pass | High |  |  | 08-10-2019 | DungND
7 | UI test | Check Display of Deactivate button | 1. User clicks on "Manage account" 2. Click on button "Guider" | Login admin'account |  | 1. Redirects to "Manage Guider Account" screen 2. Button "Reject" should be displayed in red and in the same line with guider and next to Accept button. |  | Pass | High |  |  | 08-10-2019 | DungND
8 | Function test | Check function when admin activate an account when the account is active | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | 1. Status of guider is not changed |  | Pass | High |  |  | 08-10-2019 | DangNG
9 | Function test | Check function when admin activate an account when an account is inactive | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is inactive | Login admin'account |  | 1. Status of guider is changed from in-active to active |  | Pass | High |  |  | 08-10-2019 | DangNG
10 | Function test | Check function when admin deactivate an account when an account is active | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | 1. Status of guider is changed from active to in-active |  | Pass | High |  |  | 08-10-2019 | DangNG
11 | Function test | Check function when admin deactivate an account when an account is inactive | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is inactive | Login admin'account |  | 1. Status of guider is not changed |  | Pass | High |  |  | 08-10-2019 | DangNG
12 | Database test | Check database when amin deactivate an account when the account is active | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | 1. column "active" in table "guider" is false 2. all post related to the guider: column " authorized" will be changed from true to false. |  | Pass | High |  |  | 08-10-2019 | DangNG
13 | Database test | Check database when amin deactivate an account when the account is inactive | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | nothing changed |  | Pass | High |  |  | 08-10-2019 | DangNG
14 | Database test | Check database when amin activate an account when the account is active | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | nothing changed |  | Pass | High |  |  | 08-10-2019 | DangNG
15 | Database test | Check database when amin activate an account when the account is inactive | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose a guider with status is active | Login admin'account |  | 1. column "active" in table "guider" is true 2. all post related to the guider: column " authorized" will be changed from false to true. |  | Pass | High |  |  | 08-10-2019 | DangNG

## Manage guider Post
| Module Code | Manage guider post
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 11 |  |  | 0 |  | 0 |  | 11 |  | 8 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Guider Post page | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. Guider Post is shown, including: Title, Description, Reason, Status,Activate button, Deactivate button. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 07-10-2019 | DungND
2 | UI test | Check Display of Title column | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. Title of a post should be displayed under "Title" column. |  | Pass | High |  |  | 07-10-2019 | DungND
3 | UI test | Check Display of Description column | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. Description of a post should be displayed under "Description" column. |  | Pass | High |  |  | 07-10-2019 | DungND
4 | UI test | Check Display of Reason column | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. Reason of a post should be displayed under "Reason" column. |  | Pass | High |  |  | 07-10-2019 | DungND
5 | UI test | Check Display of Status column | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. Status of a post should be displayed under "Status" column. |  | Pass | High |  |  | 07-10-2019 | DungND
6 | Function test | Check function when admin authorie a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post with status is false then click on button "Activate" | Login admin'account |  | 1. Status of the post is changed from false to true 2. The color of Activate button is blue. |  | Pass | High |  |  | 07-10-2019 | DangNG
7 | Function test | Check function when admin unauthorie a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post with status is true then click on button "Deactivate" | Login admin'account |  | 1. Status of the post is changed from true to false. 2. The color of Activate button is red. |  | Pass | High |  |  | 07-10-2019 | DangNG
8 | UI test | Check Display of Activate button | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. The color of Activate button should be in blue |  | Pass | High |  |  | 07-10-2019 | DungND
9 | UI test | Check Display of Deactivate button | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name | Login admin'account |  | 1. Redirects to "Manage Guider Post" screen 2. The color of Deactivate button should be in red |  | Pass | High |  |  | 07-10-2019 | DungND
10 | Database test | Check database when amin Activate a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post with status is true then click on button "Activate" | Login admin'account |  | 1. column "Activated" in table "post" of that post record is true |  | Pass | High |  |  | 07-10-2019 | DangNG
11 | Database test | Check database when amin Deactivate a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post with status is true then click on button "Deactivate" | Login admin'account |  | 1. column "Activated" in table "post" of that post record is false |  | Pass | High |  |  | 07-10-2019 | DangNG

## View Hide review
| Module Code | View/Hide review on a post
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 8 |  |  | 0 |  | 0 |  | 8 |  | 1 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Post review page | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. | Login admin'account |  | 1. Redirects to "Manage Post review" screen 2. Post reviewt is shown, including: Review, Show/Hide 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DungND
2 | UI test | Check Display of Title column | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. | Login admin'account |  | 1. Redirects to "Manage Post review" screen 2. Review content of a post should be displayed under "Review" column. |  | Pass | High |  |  | 08-10-2019 | DungND
3 | UI test | Check Display of Show button | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. | Login admin'account |  | 1. Redirects to "Manage Post review" screen. 2. The color of Show button should be in blue. |  | Pass | High |  |  | 08-10-2019 | DungND
4 | UI test | Check Display of Hide button | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. | Login admin'account |  | 1. Redirects to "Manage Post review" screen. 2. The color of Hide button should be in red. |  | Pass | High |  |  | 08-10-2019 | DungND
5 | Function test | Check function when admin hit button "Hide" a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. 5. Choose one post and click on "Hide" button | Login admin'account |  | 1. The color of the button changed from blue to red. 2. Button is changed from Show to Hide. |  | Pass | High |  |  | 08-10-2019 | DangNG
6 | Function test | Check function when admin hit button "Show" a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. 5. Choose one post and click on "Show" button | Login admin'account |  | 1. The color of the button changed from red to blue. 2. Button is changed from Hide to Show. |  | Pass | High |  |  | 08-10-2019 | DangNG
7 | Database test | Check database when amin hit button "Show" a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. 5. Choose one post and click on "Show" button | Login admin'account |  | 1. column "visible" in table "post" of that post record is true |  | Pass | High |  |  | 08-10-2019 | DangNG
8 | Database test | Check database when amin hit button "Hide" a post | 1. User clicks on "Manage account" 2. Click on button "Guider" 3. Choose one guider and click on Guider name 4. Choose one post and click on a post title. 5. Choose one post and click on "Show" button | Login admin'account |  | 1. column "visible" in table "post" of that post record is false |  | Pass | High |  |  | 08-10-2019 | DangNG

## Add category
| Module Code | Add category
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 10 |  |  | 0 |  | 0 |  | 10 |  | 7 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Category and category page | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. Manage Category and Location is shown, including: "Add category button",A cloumn of existing category. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 06-10-2019 | DungND
2 | UI test | Check Display of "Add category" button | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. The color of "Add category" button should be in blue. |  | Pass | High |  |  | 06-10-2019 | DungND
3 | UI test | Check Display of "Category" column | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. All existing category should be displayed in the column. |  | Pass | High |  |  | 06-10-2019 | DungND
4 | Function test | Check to see a field to add when admin click on "Add category" button | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button | Login admin's account |  | 1. Redirects to "Manage Category and Location" screen 2. A field appears so that admin can input the new category, including a text box and 2 buttons: add and close |  | Pass | High |  |  | 06-10-2019 | DangNG
5 | Function test | Check function when admin click on "close button" | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. User clcks on "Close" button | Login admin's account |  | 1. The field to input new category disappear. |  | Pass | High |  |  | 06-10-2019 | DangNG
6 | Function test | Check function when admin click on "Add" button" without input any data | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. User clicks on "Add" button | Login admin's account |  | 1. Display a error message:"please input a category". 2. Category column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
7 | Function test | Check function when admin click on "Add" button" after input a existing category | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. Input : "Food trip" in the fileld. 3. User clicks on "Add" button | Login admin's account | Food trip | 1. Display a error message:"This category is already existed". 2. Category column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
8 | Function test | Check function when admin click on "Add" button" after input a new non-existed category | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. Input : "Cycling trip" in the fileld. 3. User clicks on "Add" button | Login admin's account | Cycling trip | 1. The field to add category is hided. 2. Category column below is added with "Cycling trip" |  | Pass | High |  |  | 06-10-2019 | DangNG
9 | Database test | Check function when admin click on "Add" button" after input a new non-existed category | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. Input : "Cycling trip" in the fileld. 3. User clicks on "Add" button | Login admin's account | Cycling trip | 1. Table Category has a new record: Cycling trip. |  | Pass | High |  |  | 06-10-2019 | DangNG
10 | Function test | Check function when admin click on "Add" button" after input a category with numberic format | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add category" button 3. Input : "1234 trip" in the fileld. 3. User clicks on "Add" button | Login admin's account | 1234 trip | 1. Display a error message:"Wrong format. Please re-input". 2. Category column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG

## Add Location
| Module Code | Add location
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 18 |  |  | 0 |  | 0 |  | 18 |  | 15 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of Manage Location page | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. Manage Category and Location is shown, including: "Add Location button",A cloumn of existing location. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 06-10-2019 | DungND
2 | UI test | Check Display of "Add location" button | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. The color of "Add location" button should be in blue. |  | Pass | High |  |  | 06-10-2019 | DungND
3 | UI test | Check Display of "Location" column | 1. User clicks on "Manage Category and Location" | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. All existing category should be displayed in the column. |  | Pass | High |  |  | 06-10-2019 | DungND
4 | UI test | Check Display of when admin hit the "Add Location" button | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add location" button | Login admin'account |  | 1. Redirects to "Manage Category and Location" screen 2. A field appears so that admin can input the new location, including 3 text box ( Country, City, Place) and 2 buttons: add and close. |  | Pass | High |  |  | 06-10-2019 | DungND
5 | UI test | Check Display of "Country" text box when admin click on "Add location" button | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add location" button | Login admin'account |  | 1. Country text box should be displayed under "Add location" button and can be inputed. |  | Pass | High |  |  | 06-10-2019 | DungND
6 | UI test | Check Display of "City" text box when admin click on "Add location" button | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add location" button | Login admin'account |  | 1. City text box should be displayed under "Add location" button and can be inputed. |  | Pass | High |  |  | 06-10-2019 | DungND
7 | UI test | Check Display of "Place" text box when admin click on "Add location" button | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add location" button | Login admin'account |  | 1. Place text box should be displayed under "Add location" button and can be inputed. |  | Pass | High |  |  | 06-10-2019 | DungND
8 | Function test | Check function when admin click on "close button" | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User clcks on "Close" button | Login admin's account |  | 1. The fields to input new Location is hided. |  | Pass | High |  |  | 06-10-2019 | DangNG
9 | Function test | Check function when admin click on "Add" button without input any data in all 3 fields | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User clicks on "Add" button | Login admin's account |  | 1. Display a error message under all the fields:"please input". 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
10 | Function test | Check function when admin click on "Add" button , "Country" field is left empty. | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 2 fields : City and Place 4. User clicks on "Add" button | Login admin's account | City: 'Ha noi' Place: 'Chuong Duong Bridge' | 1. Display a error message under "Country" field:"please input". 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
11 | Function test | Check function when admin click on "Add" button , "City" field is left empty. | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 2 fields : Country and Place 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' Place: 'Chuong Duong Bridge' | 1. Display a error message under "Country" field:"please input". 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
12 | Function test | Check function when admin click on "Add" button , "Place" field is left empty. | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 2 fields : City and Country 4. User clicks on "Add" button | Login admin's account | City: 'Ha noi' Country: 'Viet nam' | 1. Display a error message under "Country" field:"please input". 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
13 | Function test | Check function when admin click on "Add" button" after input a country with numberic format | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: '123 Viet nam' City: 'Ha noi' Place: 'Chuong Duong Bridge' | 1. Display a error message:"Wrong format. Please re-input". Under "Country" text box. 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
14 | Function test | Check function when admin click on "Add" button" after input a city with numberic format | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' City: '13 Ha noi' Place: 'Chuong Duong Bridge' | 1. Display a error message:"Wrong format. Please re-input". Under "City" text box. 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
15 | Function test | Check function when admin click on "Add" button" after input a place with numberic format | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' City: 'Ha noi' Place: '123 Chuong Duong Bridge' | 1. Display a error message:"Wrong format. Please re-input". Under "Place" text box. 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
16 | Function test | Check function when admin click on "Add" button" after input a right format into all those field with non-existing place | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' City: 'Ha noi' Place: 'Chuong Duong Bridge' | 1. The field to add Location is hided. 2. Location column below is added with "Chuong Duong Bridge" |  | Pass | High |  |  | 06-10-2019 | DangNG
17 | Function test | Check function when admin click on "Add" button" after input a right format into all those field with existing place | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' City: 'Ha noi' Place: 'Long Bien Bridge' | 1. Display a error message:"This location is already existed". 2. Location column below is not changed. |  | Pass | High |  |  | 06-10-2019 | DangNG
18 | Database test | Check database when admin click on "Add" button" after input a right format into all those field with non-existing place | 1. User clicks on "Manage Category and Location" 2. User clicks on "Add Location" button 3. User input in 3 fields 4. User clicks on "Add" button | Login admin's account | Country: 'Viet nam' City: 'Ha noi' Place: 'Chuong Duong Bridge' | 1. Table Location has a new record: Chuong Duong Bridge |  | Pass | High |  |  | 06-10-2019 | DangNG

## Statistic of completed trip
| Module Code | View statistic revenuew of completed trip by month
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 2 |  |  | 0 |  | 0 |  | 2 |  | 0 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of View statistic of completetd trip by month page | 1. User clicks on "View statistic of completed trip by month" | Login admin'account |  | 1. Redirects to "Statistic of completed trip by month" screen 2. Statistic of completed trip is shown, including: chart(showing completed trip). 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DungND
2 | Function test | Check function when user click on "View statistic of completed trip by month" | 1. User clicks on "View statistic of completed trip by month" | Login admin'account |  | 1. Redirect to "Statistic of completed trip by month" 2. Showing the chart which express the revenue by month of the system. |  | Pass | High |  |  | 08-10-2019 | DangNG

## Statistic of revenue by month
| Module Code | View statistic revenuew by month
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 2 |  |  | 0 |  | 0 |  | 2 |  | 0 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of View statistic of revenue by month page | 1. User clicks on "View statistic of revenue by month" | Login admin'account |  | 1. Redirects to "Statistic of revenue by month" screen 2. Statistic of revenue is shown, including: chart(showing revenue). 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 08-10-2019 | DungND
2 | Function test | Check function when user click on "View statistic of revenu by month | 1. User clicks on "View statistic of revenue by month" | Login admin'account |  | 1. Redirect to "Statistic of revenue by month" 2. Showing the chart which express the revenue by month of the system. |  | Pass | High |  |  | 08-10-2019 | DangNG

## Login_Logout
| Module Code | Log in/Log out
Test Requirement
| Pass |  |  | Fail |  | Untested |  | Number of test case |  | High | Medium | Low
| 10 |  |  | 0 |  | 0 |  | 10 |  | 7 | 0 | 0
No | Test Type | Test case description | Steps | Pre-condition | TestData | Expected Results | Actual Results | Result | Priority | Note | Img | Date1 | Tester1
1 | UI test | Check layout of log in page | 1. Go to log in page |  |  | 1. Redirects to login screen 2. Input area and button search as the design in SRS including: username field, password field, login button 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 05-10-2019 | DangNG
2 | UI test | Check layout of user name field | 1. Go to log in page |  |  | 1. Redirects to login screen 2. Username field is showed. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 05-10-2019 | DangNG
3 | UI test | Check layout of password field | 1. Go to log in page |  |  | 1. Redirects to login screen 2. Password field is showed. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 05-10-2019 | DangNG
4 | UI test | Check layout of login button | 1. Go to log in page |  |  | 1. Redirects to login screen 2. Login button is showed. 3. Color, position, size is same as the design in SRS. |  | Pass | High |  |  | 05-10-2019 | DangNG
5 | Function test | Check function the password field will display when user input | 1.Go to log in page 2.Input password |  | passwod: 123asd | 1. The field is showed '******' instead of '123asd' |  | Pass | High |  |  | 05-10-2019 | DangNG
6 | Function test | Check function when user input wrong password | 1.Go to log in page 2.Input password and username 3.Click on "Log in" buton |  | user name: 'dung' password: '123asd' | 1. Display the error message: "the username or password is wrong" 2. Stay on log-in page. |  | Pass | High |  |  | 05-10-2019 | DangNG
7 | Function test | Check function when user click on "login" button, let user name and password field blank | 1.Go to log in page 2.Click on "Log in" button |  |  | 1. Display the error message: "the username or password is wrong" 2. Stay on log-in page. |  | Pass | High |  |  | 05-10-2019 | DangNG
8 | Function test | Check function when user click on "login" button, let user name field blank | 1.Go to log in page 2. Input password 3.Click on "Log in" button |  | password: '123asd' | 1. Display the error message: "the username is wrong" 2. Stay on log-in page. |  | Pass | High |  |  | 05-10-2019 | DangNG
9 | Function test | Check function when user click on "login" button, let password field blank | 1.Go to log in page 2. Input username 3.Click on "Log in" button |  | user name: 'dung' | 1. Display the error message: "the password is wrong" 2. Stay on log-in page. |  | Pass | High |  |  | 05-10-2019 | DangNG
10 | Function test | Check function when user click on "login" button, with correct user name and password | 1.Go to log in page 2. Input username 3.Click on "Log in" button |  | user name: admin'username password: admin'password' | 1. Redirect to admin management screen |  | Pass | High |  |  | 05-10-2019 | DangNG